## Template
Project Charter
Project Name:
Problem Statement | Business Case & Benefits
Goal Statement | Timeline
The goal is to decrease/increase ________ (unit) _________ (unit measure) from __________ (baseline) to ______________ (target) by ________ (target date) (see Goal Statement Builder Template) | Phase | Planned | Actual
Define:
Measure:
Analyze:
Improve:
Control:
Scope | Team Members
Process Start: | Position | Person | Time Commitment
Process End: | Team Lead
In: | Sponsor
Team Member
Out: | Team Member
Team Member

## Example
Project Charter
Project Name: Bahama Bistro Lunch Order Cycle Time
Problem Statement |  | Business Case & Benefits
In the last 3 months we have been receiving customer complaints about how long the food is taking to be delivered during lunch time. Current cycle time average is 28 minutes. If this continues we may lose our business customers who are on a tighter vacation schedule than our vacationers. We could lose revenue |  | Cycle Time improvement in our food orders for lunch would result in an enhanced client experience. Cycle time improvement could also translate into monetary benefits because we may turn tables quicker and seat more customers, which will increase revenue.
Goal Statement |  | Timeline
Reduce the cycle time to deliver sandwiches, salads and soups from an average of 13 minutes to 11 minutes or less. Reduce the time to deliver entrees from an average of 28 minutes to 20 minutes or less by May 10th |  | Phase | Planned | Actual
|  | Define: | January 14th | January 18th
|  | Measure: | January 30th | March 10th
|  | Analyze: | April 10th | April 12th
|  | Improve: | May 10th | May 12th
|  | Control: | June 4th | June 20th
Scope |  | Team Members
Process Start: | Customer arrives or calls | Position | Person | Time Commitment
Process End: | Deliver order (or pickup) | Team Lead | Shift Manager | 25%
In: | Food items served, process steps, length of cook time, reallocation of staff resources | Sponsor | Server | 15%
|  | Team Member | Chef | 15%
Out: | System upgrades and additional hiring, vendor processes and food delivery schedules. | Team Member | Host | 10%
|  | Team Member | Busboy | 10%

## Example 2
Project Charter
Subtitle
Problem Statement | Business Case & Benefits
Customers are complainging about how long it takes to get their pick-up orders. Currently the total lead time for pick-up orders is an average of 27 minutes | Cycle time improvement for pick-up orders will result in an enhanced client experience. Cycle Time improvement could translate into monetary benefits because we will be seen as a more consistent and reliable pick-up option, which could increase customer retention and revenue.
Goal Statement | Timeline
The goal is to reduce the pick-up order lead time from average of 27 minutes to an average of 20 minutes by the end of Q2 of this year | Phase | Planned | Acutal
| Define: | 2016-03-02 | 2016-03-04
| Measure: | 2016-03-22 | 2016-03-23
| Analyze: | 2016-04-13 | 2016-04-10
| Improve: | 2016-05-30 | 2016-05-29
| Control: | 2016-06-22 | 2016-06-24
Scope | Team Members
Process Start: Customer places and order for pick-up Process End: Customer picks up the order at the location Out: No new staff or technologies In: Job descriptions, layout, process steps | Position | Person | Time Commitment
| Team Lead | Wesley | 20%
| Sponsor | Elisabeth | 20%
| Team Member | Julie | 15%
| Team Member | Tracy | 15%
| Team Member | Scott | 15%