## Project Charter
Project Charter
Problem Statement | Business Case & Benefits
The Problem Statement should address these questions: What is wrong, not working and not meeting our customer’s needs? When and where do the problems occur? What is the frequency of the problem? What’s the impact of the problem on our customers/business or employees? What is the financial impact of the project and/or problem? | The Business Case should address these questions: Why is this project worth doing? Why is it important to do now? What are the consequences of not doing this project? How does it fit in with business initiatives and targets?
Goal Statement | Timeline
[increase/Decrease] [Unit] from a baseline of [baseline] to a target of [goal level] by [date projected to reach target level] | Phase | Planned Completion Date |  | Actual
Define:
Measure:
Analyze:
Improve:
Control:
Scope - First/Last and In/Out | Team Members
1st Process Step | Position | Person | Title | % of Time
Last Process Step | Team Lead
Sponsor
In Scope: | Team Member
Team Member
Out of Scope: | Team Member
Team Member

## Example 1
Project Charter
Lunch Order Cycle Time
Problem Statement |  | Business Case & Benefits
In the last 3 months we have been receiving customer complaints about how long the food is taking to be delivered during lunch time. Current cycle time average is 28 minutes. If this continues we may lose our business customers who are on a tighter vacation schedule than our vacationers. We could lose revenue. |  | Cycle Time improvement in our food orders for lunch would result in an enhanced client experience. Cycle time improvement could also translate into monetary benefits because we may turn tables quicker and seat more customers, which will increase revenue.
Goal Statement |  | Timeline
Reduce the average time to deliver entrees from an average of 28 minutes to 20 minutes or less by May 10th |  | Phase | Planned Completion Date |  | Actual
|  | Define: | January 14th |  | January 18th
|  | Measure: | January 30th |  | March 10th
|  | Analyze: | April 10th |  | April 12th
|  | Improve: | May 10th |  | May 12th
|  | Control: | June 4th |  | June 20th
Scope In/Out |  | Team Members
1st Process Step | Customer arrives or calls | Position | Person | Title | % of Time
Last Process Step | Deliver order (or pickup) | Team Lead | Elisabeth | Shift Manager | 20%
|  | Sponsor | Julian | Owner | 20%
In Scope: | Food items served, process steps, length of cook time, reallocation of staff resources | Team Member | Scott | Chef | 15%
Out of Scope: | System upgrades and additional hiring, vendor processes and food delivery schedules. | Team Member | Tracy | Server | 15%
|  | Team Member | Sean | Busboy | 15%

## Example 2
Project Charter
Pick-up Order Cycle Time
Problem Statement |  | Business Case & Benefits
The current total lead time for pick-up orders is an average of 27 minutes. This results in customer complaints and limits the capacity for fulfilling orders. |  | Cycle time improvement for pick-up orders will result in an enhanced client experience. Cycle Time improvement could translate into monetary benefits because we will be seen as a more consistent and reliable pick-up option, which could increase customer retention and revenue. This aligns with our mission of providing a tasty slice of island life.
Goal Statement |  | Timeline
Reduce the pick-up order lead time from average of 27 minutes to an average of 20 minutes by the end of Q2 of this year |  | Phase | Planned Completion Date |  | Actual
|  | Define: | 2016-03-02
|  | Measure: | 2016-03-22
|  | Analyze: | 2016-04-13
|  | Improve: | 2016-05-30
|  | Control: | 2016-06-22
Scope In/Out |  | Team Members
1st Process Step | Customer places and order for pick-up | Position | Person | Title | % of Time
Last Process Step | Customer picks up the order at the location | Team Lead | Wesley | Black Belt Candidate | 20%
|  | Sponsor | Elisabeth | Manager | 20%
In: | No new staff or technologies | Team Member | Julie | Processor | 15%
Out: | Job descriptions, layout, process steps | Team Member | Tracy | Waitress | 15%
|  | Team Member | Scott | Chef | 15%
|  | Team Member | Julius | Technician | 15%