## Template
Communication Plan
Stakeholder/ Stakeholder Group | Objectives (Actions Desired) | Message Content | Delivery Method(s)/Venues | By When (Frequency)
Management | Support the project | Please speak to other members of management about the need for the project how change will be good | Monthly Board Meeting | By Saturday

## Example
Communication Plan
Stakeholder/ Stakeholder Group | Objectives (Actions Desired) | Message Content | Delivery Method(s)/Venues | By When (Frequency)
Management | Support the project | Please speak to other members of management about the need for the project how change will be good | Monthly Board Meeting | By Saturday
Manager Accounts Payable | Get vendor information | Please forward the contact information of the condiment vendor | Email | By Thursday
Cashiers | Have more people able to run the register | Let us know your availability for teaching and mentoring others for Cross-Training | Morning Huddle | By Monday

## Example (2)
Communication Plan
Stakeholder/ Stakeholder Group | Objectives (Actions Desired) | Message Content | Delivery Method(s)/Venues | By When (Frequency)
Shift Supervisors | Inform of project findings, create buy-in and ownership, participate in rollout | Results of Design of Experiments (DOE), solutions selected | Schedule meeting | 15 each month starting March
Staff | Inform of project findings, instill confidence in team and process changes | Results of Design of Experiments (DOE), solutions selected | Schedule meeting | 15 each month starting March
Chef | Inform of project findings, create buy-in and ownership, participate in rollout | Pilot results, training and implementation plan | Share at staff meeting | Attend all staff meetings
Prep Kitchen Staff | Inform of project findings, create buy-in and ownership, participate in rollout | Pilot results, training and implementation plan | Share at staff meeting | Attend all staff meetings
Purchasing | Purchase new packaging materials | Purchasing changes and execution dates | Email | By June first
Pick-Up Cashiers | Inform of project findings, create buy-in and ownership, participate in rollout | Pilot results, training and implementation plan | Share at staff meeting | Attend all staff meetings