## Template
Black Belt Storyboard Checklist
Black Belt Candidate:
- Storyboard Maximum 25 slides (Appendix Maximum 10 Slides) |  |  |  | (T) = Template available
- Key "Take Away" Required on each slide (see Black Belt Storyboard Sample) |  |  |  | Green = Green Belt slides
- For requirements with more than one option - please include one or more of the options |  |  |  | Black = Black Belt slides
Introduction Phase Requirements |  |  |  |  | Slides
☐Executive Summary (T) | Note: Includes "Before & After" Project Y graphic showing improvement |  |  |  | Control 4.6
☐Key Words - Definitions of non-DMAIC, industry specific terms |  |  | ☐Black Belt Storyboard (T) |  | Control 4.7
Define Phase Requirements
☐Project Charter (T) | Note: Use Goal Statement Builder (T) to insure proper format |  |  |  | Define 2.1 - 2.19
☐VOC Translation Matrix (T) | Note: All customer requirements must be measurable |  |  |  | Define 3.32 - 3.38
☐SIPOC (T) |  |  |  |  | Define 4.24 - 4.29
☐Detailed Map (1 or more) | ☐Swimlane (T) | ☐Value Stream (T) | ☐Flow Map | ☐Spaghetti (T) | Define 4.19 - 4.48
Measure Phase Requirements
☐Data Collection Plan (T) | ☐Sample Size Calculation |  |  | Measure 4.1 - 4.31 | Measure 3.1 - 3.38
☐Measurement Systems Analysis (MSA) |  | ☐Or - an explanation of why one is not needed |  |  | Measure 3.1 - 3.33
☐Baseline Data Display | ☐Pareto | ☐Histogram | ☐Run Chart | ☐Boxplot | Analyze 3.1 3.41
Analyze Phase Requirements
☐Fishbone Diagram (T) | Note: Must include at least one ☐5 Whys (T) |  |  |  | Analyze 4.7 - 4.19
☐Project Specific Map | ☐Value-Added Flow Analysis (T) |  | ☐Other (see Define list) |  | Analyze 2.1 - 2.34
☐Null & Alt. Hypoth. Stmts | ☐Hypothesis Testing Plan (T) |  |  |  | Analyze 2.1 - 2.19
☐Verification of Root Cause | Note: Must include Hypothesis Test Results (or Regression results) |  |  |  | Analyze 2.20 - 2.56
Improve Phase Requirements
☐List of Improvements | ☐Impact Effort Matrix (T) |  | ☐Other Ranking Method |  | Improve 3.4 - 3.19
☐Implementation Plan | Note: Can include DOE, Pilot, other |  |  | Improve 2.1 - 2.66 | Improve 5.24
☐Risk Management Plan | ☐FMEA (T) | and/or | ☐Mistake-Proofing Plan |  | Improve 4.1 - 4.29
☐"To Be" Map (or segment) | ☐Swimlane (T) | ☐Value Stream (T) | ☐Flow Map | ☐Spaghetti (T) | Improve 4.1 - 4.29
☐Proof of Improvement | ☐BoxPlot | ☐Run Chart | ☐Histogram | ☐Other | Improve 4.14
Control Phase Requirements
☐Monitoring & Response Plan (T) |  |  |  |  | Control 6.3
☐Control Chart of Project Y |  |  |  |  | Control 2.1 - 2.116
☐Final Statement | ☐Lessons Learned | ☐Innovation Transfer Opportunities |  |  | Control 5.3 - 5.5