## Template
Cross-Training of Servers and Cashiers - Implementation Plan
Action Item (List steps required to implement solutions) | Responsible (List person(s) responsible for action steps) | Due Date (Indicate when action items must be completed)

## Example
Cross-Training of Servers and Cashiers - Implementation Plan
Action Item (List steps required to implement solutions) | Responsible (List person(s) responsible for action steps) | Due Date (Indicate when action items must be completed)
Meet with servers and cashiers to assess skills levels and needs | Elisabeth | June 10
Fill out the Cross-Training Matrix for each staff member | Elisabeth | June 30
Develop time table for individual training sessions and milestones | Tracy | June 15
Arrange work schedule to allow mentoring during initial cross-over | Tracy | June 17
Establish metrics and monitoring to capture opportunities for skill building | Sean | June 19
Rollout Training according to time table | Elisabeth | June 19
Meet with cashiers and servers to assess progress and need for adjustment | Elisabeth | July 15
Adjust work schedule to take advantage of cross-trained staff | Elisabeth | July 22
Determine need for continued monitoring | Tracy | July 24
Update Cross-Training Matrix | Elisabeth | July 24

## Example 2
New Pick-up Order Packaging - Implementation Plan
Action Item (List steps required to implement solutions) | Responsible (List person(s) responsible for action steps) | Due Date (Indicate when action items must be completed)
Contact Eco-Island Packaging to negotiate pricing for new containers | Tammy | June 10
Return old pick-up order packaging | Evelyn | June 30
Design visual management for packaging area | Scott | June 15
Train packaging team in new packaging process | Tammy | June 17
Run new packaging pilot | Team | June 19
Monitor packaging times for team | Evelyn | June 19
Make adjustements to packaging process based on pilot | Team | June 20
Roll-out new packaging process | Team | June 22