## 1. Screen
Screen Project Idea
Enter Project Title Below:
Cycle Time Reduction of Pick-Up Orders
Yes or No?
1. Is the word “implement” listed in the description? | No
2. Does the phrase “lack of” or "there is no" appear in the description? | No
3. Does the idea recommend starting or stopping a particular practice? | No
4. Is this process part of the candidate's regular job or are they familiar with it? | Yes
5. Is there anyone in a leadership position willing to sponsor this project? | Yes
Results: | Proceed
Instructions:
Step 1. Answer each questions with a "yes" or a "no" based on your project idea
Step 2. Check the result in the blue box
Step 3. If your project is not a solution or a decision, proceed to the next tab

## 2. Project Type
Determine Project Type
Project Title:
Cycle Time Reduction of Pick-Up Orders
Yes or No?
1. Will the project require the design of an entirely new process? | No
2. Will this project likely result in a process with little resemblance to the original process? | No
3. Is the goal of the project to implement a measurement system? | No
4. Are the root cause and solution known? | No
Project Type: | Process Improvement
Instructions:
Step 1. Answer each question with a yes or no depending on your project idea
Step 2. Check the project type in the blue box
Step 3. If the result is "Process Improvement" as a project type, proceed to the next tab

## 3. Goal
Clarify Project Goal
Project Title:
Cycle Time Reduction of Pick-Up Orders
Build the Goal Statement
The goal of this project is to: [VERB] | Enter "Decrease or Increase" | Decrease
The unit being measured in this project is:[UNIT] | Enter unit | Pick up order
The measure of this unit is: [UNIT MEASURE] | Enter Unit Measure | wait time
The estimated baseline of this measure is: [BASELINE] | Enter baseline | 15 minutes per order
The estimated target of this measure is: [TARGET] | Enter Target | 7 minutes per order
Decrease the Pick up order wait time from 15 minutes per order to 7 minutes per order
Instructions:
Step 1: Fil in each line with the term or number requested
Step 2: Estimate the baseline and target if data is currently unavailble
Step 3: Continue to the Criteria Tab
Note on C5: Enter "Decrease" or "Increase"
Note on C6: Enter the Units: Examples - Application - Order - Inventory - Invoice - Material - Product - Machine - Other: _____________
Note on C7: Enter the Unit Measure: Examples - - Cost - Revenue - Cycle Time - Defect Rate - % Good - % Bad - Other _____________
Note on C8: Enter the Baseline Examples: - 10% - $4000/month - 2 minutes per order - 30 Days - Other _______________
Note on C9: Enter the Target: Examples - - 5% - $2000/month - 1.5 minutes per order - 15 Days - 50 - Other _____________

## 4. Criteria
Project Selection Criteria
Project Title:
Cycle Time Reduction of Pick-Up Orders
Step 1: If needed, use 1-10 to change the default weights reflecting the importance of the criteria to your organization
Note: This top portion includes organizational level criteria - please score your project below
Organization Level: Impact Criteria Weighting (Weight Criteria on a Scale of 1 - 10 1 = Low Importance and 10 = High Importance) | [5 empty] | Organization Level: Effort Criteria Weighting (Weight Criteria on a Scale of 1 - 10 1 = Low Importance and 10 = High Importance)
Likely Financial Benefits | Positive Customer Impact | # of Areas Involved or Positively Impacted | Alignment with Organization Strategy | Ability to Transfer Gains to Other Processes | Level of Business Urgency | Level of IT Involvement Required | Existing Resistance to Change | Number of Areas Required to Be Involved | Potential Difficulty of Gathering Data | Capital Investment Required | Estimated Time to Implement Changes
10 | 9 | 5 | 8 | 6 | 7 | 7 | 8 | 5 | 8 | 7 | 6
Step 2: Score the project performance based on estimated impact and effort using only a 1, 3 or 5 rating
Enter Your Project Score for Each Criteria Below:
Score the Project for each Impact Criteria - 1, 3 or 5 (Higher the score - the higher the impact) | [5 empty] | Score the Project for each Effort Criteria - 1, 3 or 5 (Higher the score - the more effort required) | [5 empty] | Total | Effort | Impact
Likely Financial Benefits | Positive Customer Impact | # of Areas Involved or Positively Impacted | Alignment with Organization Strategy | Ability to Transfer Gains to Other Processes | Level of Business Urgency | Level of IT Involvement Required | Existing Resistance to Change | Number of Areas Required to Be Involved | Potential Difficulty of Gathering Data | Capital Investment Required | Estimated Time to Implement Changes
5 | 5 | 3 | 5 | 5 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | #REF! | 4.0488 | 8.9333
Step 3: Once the criteria are weighted and the project is scored, move to "Impact-Effort Matrix" tab | [12 empty] | 0 | #VALUE!
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
1
3
5

## 5. Impact-Effort Matrix
Results of Weighted Criteria Matrix
Project Title:
Cycle Time Reduction of Pick-Up Orders
| EFFORT | IMPACT
| 4.0488 | 8.9333
Notice where the project falls in the Impact/Effort Matrix: Low Effort and High Impact are "Top Picks" High Impact and High Effort are projects to "Consider" Low Effort and Low Impact might be "Potential Investments" High Effort and Low Impact are the "Least Likely" projects to pursue
TOP PICKS
CONSIDER
POTENTIAL
INVESTMENTS
LEAST
LIKELY

## 6. Project Charter
Project Charter
Cycle Time Reduction of Pick-Up Orders
Problem Statement | Business Case & Benefits
Goal Statement | Timeline
Decrease the Pick up order wait time from 15 minutes per order to 7 minutes per order | Phase | Planned | Actual
Define:
Measure:
Analyze:
Improve:
Control:
Scope In/Out | Team Members
Process Start: | Position | Person | Time Commitment
Process End: | Team Lead
Sponsor
In: | Team Member
Out: | Team Member
Team Member

## Project Sourcing Questions
Lean Six Sigma Project Sourcing Questions
– Is there an opportunity related to the organization’s business priorities?
– Is there a Scorecard or Dashboard goal that is not being met?
– Is there a failure to meet customer requirements in a specific process?
– Which process has an excessive amount of customer complaints?
– Is there an existing process with multiple hand-offs that is taking too long?
– Where do defects and rework appear most often?
– Where are the costs of rework and “Band-Aid” solutions?
– What concerns have employees and managers raised?
– What irritates employees most about the processes on which they work?
– Identify problems associated with critical or core processes:
– Excessive cycle time
– Excessive defects
– Excessive usage costs
– Excessive re-work