## Template
Action Plan
Work Area:
# | Action Items | Who | When
1 | Check with leadership to get permission to conduct 5S | Elisabeth | 2016-02-01
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Example
Action Plan
Work Area: | Lunch Prep Area
# | Action Items | Who | When
1 | Check with leadership to get permission to conduct 5S | Elisabeth | 2016-02-01
2 | Determine participants to include in 5S | Tracy | 2016-02-02
3 | Distribute 5S Manufacturing Assessment | Tracy | 2016-02-02
4 | Schedule 5S during pre-opening and send invitations | Elisabeth | 2016-02-04
5 | Order/Assemble supplies (tape, markers, bins, etc.) | Sean | 2016-02-05
6 | Conduct 5S with Team | Tracy | 2016-02-12
7 | Create ongoing audit schedule with team | Sean | 2016-02-13
8 | Conduct first audit together | Sean | 2016-03-12
9
10
11
12
13
14
15
16
17
18
19
20