## Template
Project Closure
Lessons Learned |  | Customer Impact
Do's and Don'ts for Future Efforts |  | Positive Impacts on External Customer
Final Calculations of Savings or Gains
Hard Savings/Profit Increase |  | Soft Savings - Cost or Time
Process Owner Hand-off |  | Sign-off From Project Sponsor
Has been informed of process changes: | Yes / No
Agrees to continued monitoring of new process: | Yes / No
Has received new process documentation: | Yes / No

## Example
Project Closure
Lessons Learned |  | Customer Impact
Do's and Don'ts for Future Efforts |  | Positive Impacts on External Customer
Remember to involve everyone early |  | Customers are leaving nice comments
Don't just update people once - keep doing it throughout the life of the project |  | Our rating on Yelp just went up!
The Process Walk is always a big eye opener - make sure to include line staff and management too
Be sure to give credit to everyone who came up with good ideas - credit is free!
Final Calculations of Savings or Gains
Hard Savings/Profit Increase |  | Soft Savings - Cost or Time
Production increased by 18% |  | Time savings in prep areas due to new setup - staff available to work on other tasks
Revenue has increased by an average of $3,467 per week |  | Staff satisfaction has increased
Process Owner Hand-off |  | Sign-off From Project Sponsor
Has been informed of process changes: | Yes / No | The Bahama Bistro Team did a great job! - I'm offically giving my stamp of approval for documented improvements. - Elisabeth - Bistro Manager
Agrees to continued monitoring of new process: | Yes / No
Has received new process documentation: | Yes / No

## Example 2
Project Closure
Lessons Learned |  | Customer Impact
Do's and Don'ts for Future Efforts |  | Positive Impacts on External Customer
Testing takes rigor but it helps everyone accept decisions |  | We have more pick-up order customers
Involving each department increases the overall knowledge base, and it also improves connections between staff |  | We are number one on the island again!
Design of Experiments seemed like a huge undertaking but turned out to be very manageable
Including staff in the Measurement Systems Analysis helped everyone appreciate the need for good measurement
Final Calculations of Savings or Gains
Hard Savings/Profit Increase |  | Soft Savings - Cost or Time
Pick-up order business has almost doubled |  | Time savings in Pick-Up area means more crew to help when restaurant volume requires more staff
Revenue has increased by an average of $5,127 per week
Process Owner Hand-off |  | Sign-off From Project Sponsor
Has been informed of process changes: | Yes / No | The Bahama Bistro Team did a phenomenal job! - I am happily signing off on this Black Belt project and I'm ready to assign the team to the next project! - Tracy - Staff Lead
Agrees to continued monitoring of new process: | Yes / No
Has received new process documentation: | Yes / No